## Sheet1
S. No | Submitted By | Submitted Date | Description | Detected id | Assigned To | Type of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Lavesh Kartik | 2025-08-20 | Validating Sign Up page by entering an already registered email. The system still allows registration instead of blocking with "Email already exists!" | DT001 | Rupa Shrees | Standards | Bug is accepted and fix is in progress | 2025-08-22 | Closed | No
2 | Lavesh Kartik | 2025-08-22 | Validating Sign Up page by leaving mandatory fields blank. The system accepts incomplete data instead of prompting "All required fields must be filled". | DT002 | Rupa Shrees | Standards | Bug is accepted and fix is in progress | 2025-08-25 | Closed | No
3 | Lavesh Kartik | 2025-08-26 | Validating Forgot Password page by entering a registered email. The OTP is not delivered to the user’s email. | DT003 | Siddharth Maurya | Logical | Bug is accepted and fix is in progress | 2025-08-27 | Closed | No
4 | Mourya Vardhan Rathod | 2025-08-26 | Validating Login by entering wrong credentials multiple times. Instead of locking out or showing an error, the system continues to refresh the same page without feedback. | DT004 | Siddharth Maurya | Logical | Bug is accepted and fix is in progress | 2025-08-28 | Closed | No
5 | Mourya Vardhan Rathod | 2025-08-29 | Validating Profile Edit page by entering invalid characters (like special symbols) in the phone number field. The system saves invalid data instead of rejecting it. | DT005 | Sanjana | Standards | Bug is accepted and fix is in progress | 2025-08-30 | Closed | No
6 | Mourya Vardhan Rathod | 2025-08-30 | Validating Opportunity Creation form by leaving the “Required Skills” field blank. The system still saves the opportunity without mandatory details. | DT006 | Sanjana | Standards | Bug is accepted and fix is in progress | 2025-08-31 | Closed | No
7 | Rupa Shrees | 2025-08-30 | Validating Opportunity Edit by changing the duration to negative values. The system accepts invalid input instead of throwing an error. | DT007 | Chandhrasekhar Raju | Logical | Bug is accepted and fix is in progress | 2025-08-31 | Closed | No
8 | Rupa Shrees | 2025-08-31 | Validating Opportunity Listing page. Some opportunities are not displayed in the listing even though they exist in the database. | DT008 | Chandhrasekhar Raju | Logical | Bug is accepted and fix is in progress | 2025-08-31 | Closed | No
9 | Rupa Shrees | 2025-09-01 | Validating the UI responsiveness of the Opportunity Listing page. On mobile view, text overlaps and cards are misaligned. | DT009 | Lavesh Kartik | User Interface | Bug is accepted and fix is in progress | 2025-09-02 | Closed | No
10 | Sanjana | 2025-09-02 | Validating Matching Algorithm by registering a volunteer with location and skills. The system suggests irrelevant opportunities instead of relevant matches. | DT010 | Lavesh Kartik | Logical | Bug is accepted and fix is in progress | 2025-09-04 | Closed | No
11 | Sanjana | 2025-09-02 | Validating Chat feature by sending a message between a volunteer and NGO. Messages are delayed and sometimes not delivered in real time. | DT011 | Sanjana | Logical | Bug is accepted and fix is in progress | 2025-09-04 | Closed | No
12 | Sanjana | 2025-08-03 | Validating Notification system for new opportunities. Notifications are not triggered for certain users even when a relevant match is available. | DT012 | Sanjana | Standards | Bug is accepted and fix is in progress | 2025-08-05 | Closed | No
13 | Siddharth Maurya | 2025-09-06 | Validating the UI of the Chat interface. On smaller screens, the message box overlaps the text area. | DT013 | Karampudi Riteesh | User Interface | Bug is accepted and fix is in progress | 2025-09-08 | Closed | No
14 | Siddharth Maurya | 2025-09-06 | Validating Admin Dashboard when filtering opportunities by date. Some opportunities do not appear in the report even though they match the filter. | DT014 | Karampudi Riteesh | Logical | Bug is accepted and fix is in progress | 2025-09-09 | Closed | No
15 | Siddharth Maurya | 2025-09-10 | Validating User Suspension feature. Suspended users can still log in instead of being blocked. | DT015 | Subisha | Logical | Bug is accepted and fix is in progress | 2025-09-12 | Closed | No
16 | Chandhrasekhar Raju | 2025-09-14 | Validating Report Download feature. The generated PDF report is missing user activity logs. | DT016 | Subisha | Standards | Bug is accepted and fix is in progress | 2025-09-17 | Closed | No
17 | Chandhrasekhar Raju | 2025-09-19 | Validating Analytics page. Graphs showing volunteer responses do not update when new opportunities are created. | DT017 | Lavesh Kartik | Logical | Bug is accepted and fix is in progress | 2025-09-21 | Closed | No
18 | Chandhrasekhar Raju | 2025-09-19 | Validating Admin Dashboard responsiveness. On mobile devices, charts and cards are misaligned. | DT018 | Chandhrasekhar Raju | User Interface | Bug is accepted and fix is in progress | 2025-09-21 | Closed | No
19 | Karampudi Riteesh | 2025-09-22 | Validating Opportunity Deletion feature. Deleted opportunities still appear in the volunteer’s suggestion list. | DT019 | Mourya Vardhan Rathod | Logical | Bug is accepted and fix is in progress | 2025-09-23 | Closed | No
20 | Subisha | 2025-09-24 | Validating User Activity logs. The admin panel shows incomplete data for certain users. | DT020 | Sanjana | Standards | Bug is accepted and fix is in progress | 2025-09-25 | Closed | No